## Sheet1
EXECUTION PLAN | 2023-10-02 | 2023-10-09 | 2023-10-16 | 2023-10-23 | 2023-10-30 | 2023-11-06 | 2023-11-13 | 2023-11-20 | 2023-11-27 | 2023-12-03 | Date
Status Update 1 (Project Introduction Presentation)
Build Model Scrapper
Find/Create Gensim Test Data | [9 empty] | Not Started
Build Gensim Framework | [9 empty] | In Progress
Acquire Valid Article Data for NLTK Parsing | [9 empty] | Complete
Expand Scrappers to target websites | [9 empty] | Behind Schedule
Complete NLTK text processing w/ Valid Data for Textblob
Design Blitz
Test Gensim Framework
Begin testing Textblob Sentiment scores w/ Valid Data
Acquire Preliminary data for Analyzer and Modeler
Create XGBoost Model
Find/Create Training and Validation Data for XGBoost Model
Database Creation
Status Update 2 (Project Update Presentation)
Format XGBoost Output to Narrative Curves
Verify Textblob outputs Subjectivity/Sentiment scores w/o errors
Database Verification and Migration to Olympus
Connect from Scraper to Olympus Database
Test and Validate XGBoost Model
Verify Scraper Connection Populate Database
Create tensorflow model for Emotion Recognition on articles
Apply model to extract numerical values for emotions on articles
Status Update 3 (Final Presentation)
Subsystem Demonstration
Final Report