## Sheet1
EXECUTION PLAN | 2024-01-22 | 2024-01-29 | 2024-02-05 | 2024-02-12 | 2024-02-19 | 2024-02-26 | 2024-03-04 | 2024-03-11 | 2024-03-18 | 2024-03-25 | 2024-04-01 | 2024-04-08 | 2024-04-15 | 2024-04-22 | 2024-04-29
Rescope Project for New Semester | bar: 2024-01-22
Add Text Cleaner to Scraper | bar: 2024-01-22 to 2024-01-29
Add Sentiment/Subjectivity to Narritive Modler | bar: 2024-01-22 to 2024-01-29
Validate Narrative curve model with sentiment analyzer | bar: 2024-01-29 to 2024-02-05
Verify Scrapy works with NLTK cleaner | bar: 2024-01-29 to 2024-02-05
Bi-Weekly Update 1 | bar: 2024-01-29
Connect database to Model | bar: 2024-02-05 to 2024-02-12
Fill Database with Entries | bar: 2024-02-05 to 2024-03-25
Test connection from Database to Model | bar: 2024-02-12 to 2024-02-19
Bi-Weekly Update 2 | bar: 2024-02-12
Validate test data from database works with Model | bar: 2024-02-19 to 2024-03-04
Add additional scrapers | bar: 2024-02-19 to 2024-03-04
Bi-Weekly Update 3(Blitz) | bar: 2024-02-26
Train Model with data from database | bar: 2024-02-26 to 2024-03-04
Database Cleanup | bar: 2024-03-11 to 2024-03-25
Validate Model | bar: 2024-03-11 to 2024-03-25
Bi-Weekly Update 4 | bar: 2024-03-18
Database Finalization | bar: 2024-03-18 to 2024-03-25
Extra Model Training if needed | bar: 2024-03-18 to 2024-04-01
Bi-Weekly Update 5 | bar: 2024-04-01
Creation of Technical Report for Sponsor | bar: 2024-04-01 to 2024-04-08
Create graphical output based on analyzed data from ML model | 2024-02-05: In Progress
Final Design Presentation | 2024-02-05: Complete
Final Project Demonstration | 2024-02-05: Behind Schedule
Final Report | 2024-02-05: Not Started