## Sheet1
Paragraph # | Test Name | Success Criteria | Methodology | Status | Responsible Engineer(s)
3.1.1 | Scrapper Deployment | Data acquired match target website | Manually verify that the data comes from the target | TESTED | Alexander Corpstein
3.1.1 | Scrapper Data Verification | Data acquired matches the HTML of the target website | Manually verify that the data extracted matches the target HTML | TESTED | Alexander Corpstein
3.2.3.2 | Input Data Format | Data is formatted for insertion | Verify that the data is correctly formatted for insertion into the database | TESTED | Alexander Corpstein
3.2.3 | Scrapper to Database Connection | Scraper successfully sends data to the Database | Load data from the Scrapper into the database then request the data from the database and verify the data | TESTED | Alexander Corpstein
3.1.1 | Database Creation | Database is successfully setup | Verify that the .db file is create in the correct directory in the Olympus server | TESTED | Alexander Corpstein
3.1.1 | Database Storage | Database successfully stores and outputs data | Load preselected data then request it and verify completeness | TESTED | Alexander Corpstein
3.2.3.1 | Olympus Connection | All project members can access Olympus server | Ensure that all team members can access the team directory | TESTED | Alexander Corpstein
3.2.3.2 | Communicate with SQL database | Successfully able to pull SQL data out of the database for analyzing | Create a program that is connected to the server and pulls test data to Pandas | UNTESTED | James Nieberding
3.1.3 | Pandas SQL to CSV | SQL is converted into CSV that is usable for Gensim | Manually feed data that is in the database format to Pandas to test the output | TESTED | James Nieberding
3.1.3 | Gensim Initial Framework test | Gensim successfully groups predetermined articles into topics | Create test data with predetermined data points that fit into certain topics and feed it into Gensim algorithm | TESTED | James Nieberding
3.1.3 | Gensim Final Framework test | Check topics and articles associated with each topic to ensure it sorts them correctly | Feed the algorithm unknown data and perform topic modeling | TESTED | James Nieberding
3.2.1.3 | Trained XGBoost model | Model is able to correctly accept the validation set and create predictions | Create a validation data set and feed it into the model | TESTED | James Nieberding
3.2.1.3 | XGBoost Accuracy | The model is able to replicate the shape of the sentiment narrative curves up until present day | Feed the model data up until 6 months ago | TESTED | James Nieberding
3.1.2 | NLTK Parsing/Cleaning | Successfully parse/clean data from database/internet | Remove stop words, punctuation and formatting to prepare for sentiment/subjectivity analysis | TESTED | Tyler Shippy
3.2.1.4 | Initial Textblob testing | Successfully analyze multiple sentences of text data for sentiment and subjectivity without errors | Use any large text article with predetermined scores for the sole purpose of testing scoring output | TESTED | Tyler Shippy
3.2.1.4 | Textblob testing using actual data | Successfully analyze text data from NLTK processing without any errors | Using NLTK processed data from earlier testing, produce Sentiment/Subjectivity scores for real articles | TESTED | Tyler Shippy
3.2.3.2 | Tensorflow Model Initial Test | Successfully train model with at least 70% validation accuracy | Program a tensorflow model that analyzes emotion in a text with 70% validation accuracy | TESTED | Tyler Shippy
3.1.2 | Tensorflow Model Final Test | Trained Model successfully creates accurate predictions regarding our true test set (TAMU articles) | Refine the tensorflow model and its outputs to be readable and accurate for the true test set | UNTESTED | Tyler Shippy
3.1.3 | Compile Model Data into CSV | Successfully compile numerical results into a CSV with original data | Tensorflow model, NLTK, and Textblob data is formatted properly into CSV with original articles | UNTESTED | Tyler Shippy